## Workhours
Work Hours
Date | Hours | Description
2023-01-10 | 1:00 | Creation of basic concept and communication
2023-01-14 | 2:00 | Working out a basic first version circuit
2023-01-17 | 2:30 | Drawing the circuit diagram on paper and getting first feedback
2023-01-17 | 3:00 | Writing the basic software for the arduino nano microcontroller
2023-01-17 | 1:30 | Drawing basic sketches of the design
2023-01-18 | 6:00 | Finishing the basic design and creating first version of circuit diagram
2023-01-18 | 2:00 | Continued on software
2023-01-19 | 2:00 | Designed input and output panels
2023-01-19 | 1:00 | Constructed servo mounts
2023-01-19 | 2:00 | Constructed basic case
2023-01-19 | 1:00 | Constructed servo-rail assembly
2023-01-20 | 1:00 | Writing documentation
2023-01-21 | 1:00 | Drawing sketches
2023-01-22 | 1:00 | Drawing sketches
2023-01-23 | 4:00 | Designing electronics and printing first test parts
Sum: | 1899-12-31 07:00
Formulas:
Hours = SUM(C4:[Hours, row above])